## Database
Florida's Turnpike Enterprise Design Lessons Learned
Project
Entry |  |  | FTE |  | Design |  |  |  | Primary
Date | Contract | FPID | Construction PM | Design PM | Firm | Description | Source | Key Words | Discipline | Issue Summary | Lessons Learned
2014 | E8M12 | 422349-1 | Ken Hudson | Mike Van Der Heyden | Wantman Group | PGA Blvd. Ramp Bridge Replacement | Construction - Extinguish the Torch Session III Report | Specifications | ITS | Supplemental ITS specs for sections 783, 784, 785, and 786 were omitted from the original contract documents. The contract work included ITS operations directly related to the missing/necessary specs. | The contract package should be checked to ensure it includes all necessary specifications to perform the work.
2014 | E8M12 | 422349-1 | Ken Hudson | Mike Van Der Heyden | Wantman Group | PGA Blvd. Ramp Bridge Replacement | Construction - Extinguish the Torch Session III Report | Sodding | Roadway | The Contract Plans proposed to place performance turf below the newly constructed bridge in the areas enclosed between the edge of the outside shoulder pavement and the MSE wall on both the east and west sides of the mainline. These areas will need to be maintained on a regular basis. Since the area is beneath the bridge and will receive minimal water beyond the establishment period the grass would struggle to survive. | The EOR should identify areas where grass will be unable to properly grow and provide a stabilization covering for aesthetics, maintenance, and drainage purposes.
2014 | E8M12 | 422349-1 | Ken Hudson | Mike Van Der Heyden | Wantman Group | PGA Blvd. Ramp Bridge Replacement | Construction - Extinguish the Torch Session III Report | Pavement Cracking | Geotechnical | During the driving of temporary sheet pile wall within the median, it was observed that cracks were beginning to appear longitudinally along the northbound and southbound travel lanes. Subsequent monitoring of the crack and base investigations revealed that the base was in good condition and the crack and subsequent pavement settlement occurred as a result of typical vibration during the driving and extraction of the required sheet pile wall. The cracks were temporarily sealed with RPM adhesive to prevent further water intrusion. The permanent repair involved a deep milling during the scheduled mainline milling and resurfacing operations to remove the entire thickness of asphalt and to correct the cross slope. | The cost of "zero" vibration technology is very high, but the EOR should evaluate the use of this equipment during the design phase when vibrations are expected to negatively impact the soils supporting nearby travel ways. The EOR should collect accurate and detailed sub‐soil information. The EOR should prepare contingency plans for cracks forming in the roadway or pavement during any sub‐soil affecting activities.
2014 | E8M12 | 422349-1 | Ken Hudson | Mike Van Der Heyden | Wantman Group | PGA Blvd. Ramp Bridge Replacement | Construction - Extinguish the Torch Session III Report | Existing Lighting | Lighting | An inspection of existing site conditions revealed that an existing power source was in poor condition and unsafe to perform the proposed work. It was also noted that the existing load center, including the electrical panel board and the cabinet, could not accommodate the proposed circuits for new under‐deck and roadway lighting. The EOR anticipated that the existing lighting system would function independently of the new lighting system and remain operational during construction. The EOR also anticipated that the existing lighting systems along the east and west sides of the mainline were connected through an underground conduit crossing the mainline; however, it was discovered that they were connected through the traffic railing of the existing bridge structure which was scheduled to be demolished. The existing lighting system on the north side of the bridge was powered through the conduits within the slopes of the bridge which would also be removed during the demolition. Due to different conductor sizes (No. 2 existing and No. 6 proposed), any tie‐in between the existing and new systems would not be possible. The removal of existing bridge structure and slopes necessitated the installation of new No. 2 conductors. | The EOR should conduct an in‐depth review of the existing lighting system in order to properly design a safe supplemental system.
2014 | E8M12 | 422349-1 | Ken Hudson | Mike Van Der Heyden | Wantman Group | PGA Blvd. Ramp Bridge Replacement | Construction - Extinguish the Torch Session III Report | Existing Pavement Condition | Roadway | During clearing and grubbing, the contractor encountered an excessive thickness of existing asphalt on the approaches to the bridge (between 12” and 20”). It was determined that this extra depth was due to a previous bridge‐jacking operation. The existing approaches had been raised to a new elevation utilizing layers of asphalt pavement in order to achieve the final profile grade. This excessive thickness of asphalt was not denoted in the Contract Plans and could not have been expected. The contractor's scheduled plan of operation was to remove the expected asphalt with a small reclaimer machine and utilize the millings in the fill as regular embankment material. The contractor was directed to mobilize a large milling machine onsite, which allow the milled material to remain onsite and be incorporated into the embankment operations as anticipated at the time of bid. | The EOR should conduct an in‐depth review of any and all previous work within the project’s limits to ensure there is a minimal amount of differing site conditions during the construction operations.
2014 | E8M12 | 422349-1 | Ken Hudson | Mike Van Der Heyden | Wantman Group | PGA Blvd. Ramp Bridge Replacement | Construction - Extinguish the Torch Session III Report | Traffic Control Plans | Roadway | The Traffic Control Plans included a note requiring the contractor to make provisions for a law enforcement officer for all lane closures, with the 102‐14 pay item for the payment of such. The designer’s estimate omitted many of the operations that require lane closures including TBW placement, resource delivery, equipment/material staging, equipment/material movements etc. The quantified amount of man‐hours necessary for the included operations was inaccurate and in conversations with the EOR it appears that the quantity was based on an estimate on probable operations and durations and not an all‐inclusive in‐depth calculation. This oversight resulted in a final quantity 3 times greater than the contract plan quantity. | Since FTE requires all lane closures to be accompanied by an FHP Traffic Control Officer and includes the pay item for them, an accurate calculation must be made by the EOR to determine the needed amount. In order to reduce the cost of traffic control officers, the EOR can continue to include the note requiring the need for the officer during ALL lane closures but include in the note that the cost will be included in the maintenance of traffic lump sum pay item.
2014 | E8M12 | 422349-1 | Ken Hudson | Mike Van Der Heyden | Wantman Group | PGA Blvd. Ramp Bridge Replacement | Construction - Extinguish the Torch Session III Report | Pay Items | Roadway | The Contract Plans, in Phase 1 – Step 1, required the contractor to remove the existing rumble strips within the limits of the mainline traffic shift to allow for the construction of the new pier within the median of the mainline. Per the phase notes in the Contract Plans, in Phase 4 the contractor was required to re‐install the rumble strips at the locations where the rumble strips were removed for the shift. However, the Contract Plans did not include the pay item needed to compensate the contractor for the installation of the rumble strips nor a pay item footnote to indicate that this work was included in another pay item. | The EOR should ensure that method of payments are provided in the Contract Plans and/or a note depicting if the method of payment is inclusive to another pay item.
2014 | E8M52 | 429330-1 | Ken Hudson | James Kervin | Wantman Group | Indiantown Road Interchange Improvements | Construction - Extinguish the Torch Session III Report | Positive Drainage | Drainage | Maintaining positive drainage is critical to design. This is often overlooked when there is a critical section for drainage located between roadway cross sections. Specifically, the right side of a variable height barrier wall was the flow line for the off-ramp and the left side was the high side for the on‐ramp. The difference of elevation was approximately 1.5’, which meant that the embankment slope of 1:6 would bring the toe of slope out 6.5’. With no direction included in the Contract Plans, the toe of the embankment would create a dam for the off‐ramp runoff. The solution developed with the contractor was to extend the barrier wall approximately 5’ and construct a miscellaneous asphalt slope pavement apron and spill pad, which allowed the grass swale to be formed at plan location and eliminated erosion issues. | The EOR should analyze each specific outflow for positive drainage and determine if there are erosion or maintenance issues that need to be addressed. Terminal inlets may be necessary at the end of barrier walls. Issues may not readily present themselves when the outflow is located between cross sections. Both the interim and permanent condition need to be evaluated and attention needs to be provided to not only onsite conveyance but maintaining existing offsite flows as well.
2014 | E8M52 | 429330-1 | Ken Hudson | James Kervin | Wantman Group | Indiantown Road Interchange Improvements | Construction - Extinguish the Torch Session III Report | Lighting Design | Lighting | Two non‐standard 50’ light poles were proposed with twin bull horn fixtures and offsets of 60’ and 80’ to avoid existing gas lines and maintain adequate lighting levels for a ramp. Design Standard 17515 for standard aluminum light poles includes a 13.5” diameter bolt circle which is installed on top of a transformer base with a bottom bolt circle of 15” that is connected to the foundation. Due to the offsets, the shop drawing submitted and approved specified a pole bolt circle diameter of 15” instead of the standard 13.5”, which will not fit a standard T‐base. Therefore, if the light pole needed to be replaced in the future, the pole could not be reused and may not be in‐stock for quick replacement. | The EOR should, whenever possible, ensure standard dimensions are submitted and approved in the shop drawing approval process. Coordinate with FTE Maintenance on frequently damaged and replaced items that are non‐standard.
2014 | E8M52 | 429330-1 | Ken Hudson | James Kervin | Wantman Group | Indiantown Road Interchange Improvements | Construction - Extinguish the Torch Session III Report | Plan Notes | Roadway | Mainline milling and resurfacing for northbound lanes and the inside shoulder, for the purposes of traffic control, were not shown in the Typical Sections or Roadway Plans. Instead they were detailed with a note in the Traffic Control Plans. Since this project was a Lump Sum Alternative Bidding, neither pay item numbers nor bid item notes were provided to help enforce certain specification requirements typically required for permanent features. This could have been exploited by the contractor as “Temporary Pavement” was indicated in the Traffic Control Plan notes. Other features that were tied into this operation were rumble strips and final striping/thermoplastic. Additional notes were included in the as‐built plans to clarify the permanent features. | The EOR should incorporate permanent features into the Roadway Plans. When alternative lump sum bidding is utilized, be aware that conventional requirements typically covered with listing pay items could be missed.
2014 | E8M52 | 429330-1 | Ken Hudson | James Kervin | Wantman Group | Indiantown Road Interchange Improvements | Construction - Extinguish the Torch Session III Report | Signing | Traffic Design | Existing median separator for Indiantown Rd. is 6’ wide with architectural pavers. The Contract Plans specified 36” wide sign panels which would breach the standard 2’ minimum clear space from the edge of sign panel to the face of curb. This standard requirement is important to maintenance as these signs are hit often. Also, the exit gore sign was indicated by pay item 700‐20‐15. The EOR chose this pay item due to the sign panel size of 6’‐6” x 5’‐0”, or 32.5 SF. However, the Design Standard 11860 “Single Column Ground Signs” does not accommodate a panel size greater than 30 SF or width exceeding 60". At 78” wide, the sign requires a special design. The solution at the time of discovery was to proceed with a multi‐column sign assembly per current Design Standards. | The EOR should ensure sign design standards are achievable when specifying sign panel sizes.
2014 | E8M59 | 427325-1 | Joseph Chinelly/ Todd Kelly | Pamela Nagot | WBQ | Polk Parkway Painting of Bridges 160240, 160245 and 160246 | Construction - Extinguish the Torch Session III Report | Bridge Painting | Structures Maintenance | Contract Plan notes call for standard paints 595B-34491 and 595B-35488 on bridge steel beams, which are flat finish paints. However, standard paints 595B-24491 and 595B-25488 are the lowest sheen polyurethane paints available in an FDOT approved product, which are semi-gloss paints. The language in the Plan Notes was changed to allow for use of the semi-gloss paint. | When Contract Plan notes are being developed, the EOR should be sure to call for APL products.
2014 | E8M59 | 427325-1 | Joseph Chinelly/ Todd Kelly | Pamela Nagot | WBQ | Polk Parkway Painting of Bridges 160240, 160245 and 160246 | Construction - Extinguish the Torch Session III Report | Bridge Painting | Structures Maintenance | The contractor indicated that on previous projects where there were a large number of imperfections on the beam surfaces, applying a clear coat acted to highlight and amplify imperfections on the surface; often looking worse than it had prior to being re-painted. This issue did not occur, as the steel beams on this project were relatively free of surface imperfections. | Where there are a large number of surface imperfections, consider the total removal of the existing paint, down to bare metal. A grading scale for surface conditions may be necessary.
2014 | E8M79 | 431079-1, 431079-3 | Ken Hudson | Terry Miller | Moffatt & Nichol | Resurface Mainline from Glades Rd. (MP 76.2) to S. of Atlantic Ave. (MP 81.1) | Construction - Extinguish the Torch Session III Report | Pavement Design | Roadway | The trench repair detail called for a 24" wide trench; however, to achieve density requirements and based on the contractor’s available equipment, the trench width was too small. The trench width was increased to 27"+/‐ to allow the contractor’s equipment to access the trench and properly achieve density. Density could have also been achieved by using smaller lift thickness, but the operation would have taken longer, which is a greater impact to the motorist. | The industry has 24"-wide compactors, but are not readily available, typical ones are 26”-wide. The repair procedure was successful and should be used in other projects; to avoid potential claims, the repair trench width should be increased to 27”.
2014 | E8M79 | 431079-1, 431079-3 | Ken Hudson | Terry Miller | Moffatt & Nichol | Resurface Mainline from Glades Rd. (MP 76.2) to S. of Atlantic Ave. (MP 81.1) | Construction - Extinguish the Torch Session III Report | Pavement Markings | Traffic Design | The shoulder width throughout the project varied from 10’ standard (+/‐) 0”‐8”, which made it difficult to maintain the standard detail. This was even more of a challenge at bridge approaches as well as at the beginning and ending of the project limits. | For bridge approaches the EOR should prepare a typical detail that tapers the FC to meet the existing bridge edge line configuration in order to keep the edge line completely on the FC and maintain compliance with the index requirements.
2014 | E8M79 | 431079-1, 431079-3 | Ken Hudson | Terry Miller | Moffatt & Nichol | Resurface Mainline from Glades Rd. (MP 76.2) to S. of Atlantic Ave. (MP 81.1) | Construction - Extinguish the Torch Session III Report | Bridge Joints | Structures | The joint installer is claiming unforeseen conditions based on the significant difference between the theoretical joint thicknesses and actual field conditions. Although the Contract Plans require the contractor to verify the thickness prior to initiating the operation, it does not provide for compensation if there is an overrun based on thickness. The contractor assumed a theoretical thickness of 2” and applied 1.5” overbuild after milling, ¾” FC, and deduced that the final thickness would be 2.75”; however, the actual thickness for the joint was between 3.5” – 4”. The CEI indicated this is common on rehab projects; the bridge design engineers place the 2”(min) on the detail simply to address the design criteria, not as a threshold for estimating labor and materials. | The EOR should take several cores during the design phase and the results provided in the Contract Plans for estimating purposes.
2015 | E8N22 | 429025-1 | Tracie Rose | Pam Nagot | Michael Baker Jr. | Resurface Suncoast Pkwy. from Van Dyke Rd. (MP 14.2) to Paso Co. Line (MP 17.4) | Construction - Extinguish the Torch Session III Report | Existing Pavement Condition | Project Manager | Prior to construction, the CEI observed areas with severe alligator cracking. Additional coring was performed and the results required the depth of milling/resurfacing to be increased. | It is critical that roadway repairs performed through maintenance contracts be communicated to FTE Materials and FTE Roadway Design for review of pavement deterioration. For M&R projects, a project review by the EOR, FTE Maintenance and FTE Materials should be conducted six months prior to letting to determine if the Contract Plans adequately address issues which may have arisen between the initial evaluation and when the design phase is at 100% and letting is scheduled.
2015 | E8N22 | 429025-1 | Tracie Rose | Pam Nagot | Michael Baker Jr. | Resurface Suncoast Pkwy. from Van Dyke Rd. (MP 14.2) to Paso Co. Line (MP 17.4) | Construction - Extinguish the Torch Session III Report | Pavement Design | Roadway | The Contract Plans called for Traffic Level A pavement on the mainline shoulders. The contractor requested to change the shoulder pavement to Traffic Level B, which was approved. | Although the pavement design for the shoulders was adequate, contractor’s do not like to produce a different traffic level asphalt for projects. The specifications do not allow the contractor to switch traffic levels by more than one level.
2015 | E8N22 | 429025-1 | Tracie Rose | Pam Nagot | Michael Baker Jr. | Resurface Suncoast Pkwy. from Van Dyke Rd. (MP 14.2) to Paso Co. Line (MP 17.4) | Construction - Extinguish the Torch Session III Report | Sodding | Roadway | The Contract Plans included, in the typical sections, sodding over a larger area than clearing and grubbing. It was agreed that the Contractor would be paid for clearing and grubbing the entire sodded area, versus placing sod on top of existing grass. | As areas may change during Contract Plan reviews prior to letting, the EOR needs to assure both pay items for clearing/grubbing and placement of sod are addressed.
2015 | E8N22 | 429025-1 | Tracie Rose | Pam Nagot | Michael Baker Jr. | Resurface Suncoast Pkwy. from Van Dyke Rd. (MP 14.2) to Paso Co. Line (MP 17.4) | Construction - Extinguish the Torch Session III Report | Organic Soil Layer | Maintenance | Pre-bid questions received regarding the finished soil layer resulted in an increase to Pay Item 120-1 regarding placement of 6" of organic material without removing the material in place. The intent was to establish 6" of soil with an organic material content meeting the organic soil layer specifications. During construction, the contractor indicated that the Truck Borrow Pay Item 120-2-2 needed to also increase, because they bid it to excavate and then bring in premixed material and that Pay Item 162-1-11 was just for the mixing in the organics. To meet the original intent, the shoulders were constructed using Standard Index 105, Treatment I. The organics for the median, excluding the shoulders, were increased by the contractor purchasing the organics and mixing it with existing top 6" of existing material. | Do not try to increase the organics to above 10% per Specification, as areas where traffic/maintenance vehicles could be, it is too soft, may rut easily and after time will break down. In cases where the organics need to be increased, add a pay item note requiring a specified organic content for the area of concern.
2015 | E8N22 | 429025-1 | Tracie Rose | Pam Nagot | Michael Baker Jr. | Resurface Suncoast Pkwy. from Van Dyke Rd. (MP 14.2) to Paso Co. Line (MP 17.4) | Construction - Extinguish the Torch Session III Report | Cable Barrier | Roadway | Specification 540-2.5 indicates: “Provide retro-reflective sheeting… Use colorless (white) sheeting on posts installed to the right of approaching traffic and yellow sheeting on posts installed to the left of approaching traffic. Install sheeting only on one side of the posts unless otherwise specified in the plans…” For this project, the high tension cable barrier is placed in the median area, and there is at least some distance where the cable is between the two directions of traffic. | Where the high tension cable barrier called for in the median, reflectors should be specified on both sides of the posts in the Contract Plans.
2015 | E8N22 | 429025-1 | Tracie Rose | Pam Nagot | Michael Baker Jr. | Resurface Suncoast Pkwy. from Van Dyke Rd. (MP 14.2) to Paso Co. Line (MP 17.4) | Construction - Extinguish the Torch Session III Report | Guardrail | Roadway | The Suncoast Pkwy. is specified as a Scenic Highway and there are Aesthetic Guidelines to be adhered to. Existing guardrail posts are wood. The Contract Plans did not specify that guardrail posts were to be wood. Since the Aesthetic Guidelines do not specifically require wood, the Department had to request a change to the contract to have wood posts installed. | If the intent is to install wood posts, or maintain aesthetic features along a corridor, Contract Plan notes should be specific regarding the expectation for construction materials, etc.
2015 | E8N22 | 429025-1 | Tracie Rose | Pam Nagot | Michael Baker Jr. | Resurface Suncoast Pkwy. from Van Dyke Rd. (MP 14.2) to Paso Co. Line (MP 17.4) | Construction - Extinguish the Torch Session III Report | Guardrail | Roadway | Attenuators in the Contract Plans had to be adjusted due to conflicts with existing signs. The removal of guardrail end treatments was not consistently included in the pay item quantity. | EOR should ensure that there is a field verification of existing conditions to avoid design conflicts.
2015 | E8M46 | 427324-1, 427324-3 | Tracie Rose | Rebecca Bolan | Michael Baker Jr. | Resurface Suncoast Pkwy. from CR 578 (MP 37) to SR 50 (MP 46) | Construction - Extinguish the Torch Session III Report | Cable Barrier | Roadway | While excavating for the foundations of each cable barrier post, debris, drainage and utilities were encountered at fourteen locations. Posts were added to the system to avoid the conflict areas, while maintaining the minimum spacing and avoiding costs associated with designing, approving and installing shallow foundations at the conflict areas. | Include additional cable barrier posts in the Contract Plans to avoid conflicts or include a note in the Contract Plans that spacing may vary to avoid installation of floating posts for underground conflicts.
2015 | E8M46 | 427324-1, 427324-3 | Tracie Rose | Rebecca Bolan | Michael Baker Jr. | Resurface Suncoast Pkwy. from CR 578 (MP 37) to SR 50 (MP 46) | Construction - Extinguish the Torch Session III Report | Cable Barrier | Roadway | Direct sheet flow of water from the roadway eroded the embankment surrounding the cable barrier socketed posts. Additional misc. asphalt was placed to completely fill any gaps between the socket and the asphalt pad to prevent erosion. | Include additional misc. asphalt to accommodate the wider cable barrier sockets, especially in areas of steeper slopes, to prevent erosion.
2015 | E8M46 | 427324-1, 427324-3 | Tracie Rose | Rebecca Bolan | Michael Baker Jr. | Resurface Suncoast Pkwy. from CR 578 (MP 37) to SR 50 (MP 46) | Construction - Extinguish the Torch Session III Report | Pavement Design | Roadway | The base thickness varied along the profile, leading to areas of scabbing when the contractor milled into the first existing layer of structural course assumed to be of constant thickness. Areas where scabbing occurred were corrected with milling down to the lime rock and placing structural course in two lifts where appropriate. | The pavement design should not leave a minimal layer of existing asphalt during milling operations. If possible, review asphalt cores to determine where the original asphalt layers were created to set milling depths.
2015 | E8M46 | 427324-1, 427324-3 | Tracie Rose | Rebecca Bolan | Michael Baker Jr. | Resurface Suncoast Pkwy. from CR 578 (MP 37) to SR 50 (MP 46) | Construction - Extinguish the Torch Session III Report | Traffic Control Plans | Roadway | The distance between exits created significant detour routes during ramp closures. | Where the detour required is significant, the EOR should review the design for alternatives to closing the ramp (ie, provide temporary pavement, etc.).
2015 | E8M47 | 427324-4, 427324-6 | Tracie Rose | Rebecca Bolan | Michael Baker Jr. | Resurface Suncoast Pkwy. from SR 50 (MP 46) to N. Oak Hammock Plaza (MP 55) & Drainage Improvements | Construction - Extinguish the Torch Session III Report | Guardrail | Roadway | On previous Suncoast projects the guardrail finish experienced problems with the coloring and fading. The stained guardrail was removed from the contract and galvanized guardrail was installed, which resulted in a cost savings. | If staining is desired, the less expensive option is for the contractor to install galvanized guardrail and at a later date apply a stain.
2015 | E8M47 | 427324-4, 427324-6 | Tracie Rose | Rebecca Bolan | Michael Baker Jr. | Resurface Suncoast Pkwy. from SR 50 (MP 46) to N. Oak Hammock Plaza (MP 55) & Drainage Improvements | Construction - Extinguish the Torch Session III Report | Traffic Control Plans | Roadway | The distance between exits created significant detour routes during ramp closures. | Where the detour required is significant, the EOR should review the design for alternatives to closing the ramp (ie, provide temporary pavement, etc.).
2015 | E8M47 | 427324-4, 427324-6 | Tracie Rose | Rebecca Bolan | Michael Baker Jr. | Resurface Suncoast Pkwy. from SR 50 (MP 46) to N. Oak Hammock Plaza (MP 55) & Drainage Improvements | Construction - Extinguish the Torch Session III Report | Multi-Use Trail | Roadway | Construction activities impacted access to and use of the existing multi-use trail. Orange fencing used to close the trail was cut by the users. The trail was closed during peak weekend usage periods. Construction equipment was continuously crossing the trail due to adjacent staging areas. | The EOR should provide better details for barriers to be installed when closing a trail and provide specific Contract Plan notes to detail trail closure durations and limitations of construction operations. Restrict project staging areas that would impact trail operations.
2015 | E8M47 | 427324-4, 427324-6 | Tracie Rose | Rebecca Bolan | Michael Baker Jr. | Resurface Suncoast Pkwy. from SR 50 (MP 46) to N. Oak Hammock Plaza (MP 55) & Drainage Improvements | Construction - Extinguish the Torch Session III Report | Maintenance | Drainage | Two double 48" cross drains were added adjacent to two existing 48" pipes, with minimal separation between them. A precast headwall was allowed for the new construction but with no provision to connect the two structures, leaving a small area of earth that will not be able to be maintained. | The EOR should provide details in the Contract Plans to address the gap between adjacent drainage structures and coordinate a solution with FTE Maintenance.
2015 | E8M47 | 427324-4, 427324-6 | Tracie Rose | Rebecca Bolan | Michael Baker Jr. | Resurface Suncoast Pkwy. from SR 50 (MP 46) to N. Oak Hammock Plaza (MP 55) & Drainage Improvements | Construction - Extinguish the Torch Session III Report | Transition Area | Roadway | The tie-in point between the resurfacing project and the adjacent drainage improvement project did not provide for a smooth transition between the two projects. | The EOR should provide additional survey and details to ensure that the contractor has enough information to provide a smooth transverse joint between existing and new construction.
2015 | E8M50 | 429331-1, 429332-1 | Joseph Chinelly | Pamela Nagot | GAI | SR 91 at I-4 Interchange Improvements (Design-Build) | Construction - Extinguish the Torch Session III Report | Contamination | Environmental Management | During construction high concentrations of hazardous material vapors were encountered. Construction activities were suspended until a hazard assessment could be performed. The contractor initially indicated that only two feet of material was to be removed so only that strata of material was tested. It was later determined that the two feet of material to be removed was actually two feet below final proposed elevation which was deeper than the existing elevation. FTE EMO staff had to return, test and remove additional material. | Make sure to include all pertinent documentation related to contamination sites in the RFP. If contamination is encountered and remediation is necessary, assure adequate survey info is available to assess the scope of the impact.
2015 | E8M50 | 429331-1, 429332-1 | Joseph Chinelly | Pamela Nagot | GAI | SR 91 at I-4 Interchange Improvements (Design-Build) | Construction - Extinguish the Torch Session III Report | Power Service | Electrical | A load center that provides power to a flashing beacon sign arrived with a 480 V/240 V rating. The beacon sign requires a 240 V/120V service. Using the load center delivered to the site would require a step-down transformer, which FTE Maintenance prefers not to use given known maintenance issues. | EOR should verify power service needs and confirm in the Contract Plans. FTE Maintenance preference is no step-down transformers.
2015 | E8M50 | 429331-1, 429332-1 | Joseph Chinelly | Pamela Nagot | GAI | SR 91 at I-4 Interchange Improvements (Design-Build) | Construction - Extinguish the Torch Session III Report | Traffic Control Plans | Roadway | The Traffic Control Plans did not address the maintenance of traffic at the tie-in to a connector road where two ramps merge. The D-B Firm Technical Proposal indicated the need for 7" of overbuild but in the final design 16" of overbuild were required. It was determined that because of the thickness of the asphalt and drop off conditions, traffic on both ramps would have to be detoured to allow enough time to construct the overbuild. | Closer attention should be paid to overbuild design cross sections and the associated, required maintenance of traffic. Traffic Control Plans cross sections should be provided in final design at critical points like this connector road ramp merge.
2015 | E8N21 | 429023-1, 429023-3 | Todd Kelly | Pamela Nagot | Dewberry | Resurface Seminole Expy. from US 17-92 (MP 50) to I-4 (MP 55) | Construction - Extinguish the Torch Session III Report | Traffic Control Plans | Roadway | Contract Plans called for milling inside shoulder rumble strips and replacing with asphalt to ensure a smooth riding surface during temporary traffic shifts to the shoulder. This requires an entire Traffic Control Plans phase to prevent a temporary and unlikely smoothness issue. After coordination with the EOR and FTE Bituminous Engineer, it was agreed to simply pave over the rumble strips, without milling them out. | When the Traffic Control Plans calls for traffic to be temporarily shifted to the shoulder, for short periods and at lower speeds, pave over the rumble strips instead of milling and paving. The low traffic volumes should not cause the underlying rumble strips to reflect in such a short period of time.
2015 | E8N21 | 429023-1, 429023-3 | Todd Kelly | Pamela Nagot | Dewberry | Resurface Seminole Expy. from US 17-92 (MP 50) to I-4 (MP 55) | Construction - Extinguish the Torch Session III Report | Temporary Lighting | Lighting | No temporary lighting or means of payment was identified in the Contract Plans for ramp construction, which only called for existing lighting to be relocated. It was determined that temporary lighting would be required during the ramp’s 1st construction phase. | On any project with lighting pay-items, the EOR should evaluate the need for temporary lighting, identify the requirements, and provide the necessary notes, specs, and pay items to allow the contractor to properly bid the item.
2015 | E8N21 | 429023-1, 429023-3 | Todd Kelly | Pamela Nagot | Dewberry | Resurface Seminole Expy. from US 17-92 (MP 50) to I-4 (MP 55) | Construction - Extinguish the Torch Session III Report | Lighting Design | Lighting | The Contract Plans called for relocating lighting, but the existing bases were not reusable, as they did not meet the current standard for wind loading (screw bases & embedment on a steeper slope). A supplemental agreement was processed with the contractor for the addition of new bases to support the relocated poles. | For any relocation of existing lighting, the EOR should evaluate whether the existing bases are reusable and if not, identify the need for new bases in the Contract Plans.
2015 | E8N21 | 429023-1, 429023-3 | Todd Kelly | Pamela Nagot | Dewberry | Resurface Seminole Expy. from US 17-92 (MP 50) to I-4 (MP 55) | Construction - Extinguish the Torch Session III Report | Lane Closures | Traffic Operations | Paving operations were halted by ongoing wet & cold conditions, in tandem with lane closure restrictions limiting work to night time operations. September 2014 was a historically rainy month, and storms developed nearly every day near the allowable lane closure time. FTE Traffic Operations evaluated traffic volumes and daytime lane closures were ultimately allowed, thus allowing work in favorable temperatures and outside of rain events. | Additional lane closure times should be considered where there are low traffic volumes, based on potential weather delays. Resurfacing projects should be scheduled for completion in warmer months, with consideration of weather and holidays possibly pushing the completion into unfavorable paving conditions.
2015 | E8L90 | 423199-1, 423199-3 | Joseph Chinelly | Craig Bostic | Kimley-Horn | Resurface Polk Pkwy. from MP 8.1 to MP 21.7 | Construction - Extinguish the Torch Session III Report | Base Repair | Roadway | Failing base material was required to be repaired as part of the resurfacing project. Several areas required full base removal and subgrade remediation (in this case excavating 19.75"). Issues were encountered when attempting to excavate the failing base with a small capacity loader that consumed a large amount of time. Subsequent excavation was completed with a milling machine, resulting in significant time savings. | EOR should require the contractor to use a milling machine when excavating for full base removal.
2015 | E8L90 | 423199-1, 423199-3 | Joseph Chinelly | Craig Bostic | Kimley-Horn | Resurface Polk Pkwy. from MP 8.1 to MP 21.7 | Construction - Extinguish the Torch Session III Report | Base Repair | Roadway | Failing base material was required to be repaired as part of the resurfacing project. Several areas required full base removal and subgrade remediation. During a 5-month period between the base repair operation and paving of adjacent lanes, water had collected in the gravel fill. The water did not percolate through the subgrade due to high clay content in the existing soils. In subsequent base repair areas, weep trenches were constructed across the paved shoulder in order to allow water to flow through the gravel fill and drain. | When base repair is required which includes the placement of a layer of gravel fill, the EOR should specify in the Contract Plans the construction of weep trenches to allow a pathway for water to flow from under the roadway into the grassed shoulder or median.
2015 | E8L90 | 423199-1, 423199-3 | Joseph Chinelly | Craig Bostic | Kimley-Horn | Resurface Polk Pkwy. from MP 8.1 to MP 21.7 | Construction - Extinguish the Torch Session III Report | Pavement Markings | Traffic Design | The contractor re-striped the final lift of structural course according to the Contract Plans. A Plan revision was then issued, calling for the friction course to be striped with a new configuration. Since the contractor placed frication course one lane at a time it would result in one lane being striped according to the revision and the other lane(s) striped according to the old configuration, creating conflicting striping in several areas. The contractor was required to hydro-blast striping from final lift of structural course and have it re-striped according to the new configuration. | EOR should specify in the Contract Plans that any reconfiguration of existing striping should be implemented immediately following the initial milling and resurfacing.
2015 | E8L90 | 423199-1, 423199-3 | Joseph Chinelly | Craig Bostic | Kimley-Horn | Resurface Polk Pkwy. from MP 8.1 to MP 21.7 | Construction - Extinguish the Torch Session III Report | Traffic Control Plans | Roadway | Traffic Control Plans required the installation of temporary K-wall, which would be pinned per index 414. Maintenance of traffic phasing would require pinning to be performed in a live traffic lane, creating a safety issue. An alternative Traffic Control Plans was developed by the CEI and EOR that eliminated the need for pinning the barrier wall by providing an additional 2' of shoulder pavement, thus providing for a 2' offset from the barrier wall to the pavement repair drop off such that pinning is not required. | EOR should review the Traffic Control Plans to identify if additional maintenance of traffic sub-phases are required to account for activities such as pinning of temporary K-wall on the traffic side of the wall.
2015 | E8L90 | 423199-1, 423199-3 | Joseph Chinelly | Craig Bostic | Kimley-Horn | Resurface Polk Pkwy. from MP 8.1 to MP 21.7 | Construction - Extinguish the Torch Session III Report | Existing Pavement Condition | Roadway | EOR used Falling Weight Deflectometer (FWD) test to analyze condition of pavement and base. State Materials Office, during construction, conducted additional FWD testing at more frequent intervals. In several areas the limits of base and subgrade remediation extended beyond that called for in the Contract Plans due to the existing base being saturated and yielding. The FWD did accurately identify areas as having weak base material but there were many areas of weak base that were not identified by FWD testing. | EOR should not rely solely upon the FWD test results as an indicator of areas where base remediation is required. It should be used along with detailed surveys of pavement distress patterns, measurement of the in-situ moisture content of the base and (if possible) proof rolling of the base.
2015 | E8L99 | 415462-2 | Jaime Gomez | Mike Van Der Heyden | RS&H | All Electronic Toll (AET) Phase 4A | Construction - Extinguish the Torch Session III Report | Traffic Control Plans | Roadway | Traffic Control Plans did not specify hours/days for full ramp closures within the project limits. The contractor claimed hours provided during construction were not anticipated and not equivalent to a full work shift. | If scope of work requires full ramp closures, EOR should include in the Traffic Control Plans specific closure hours and days allowed for each ramp impacted. The Traffic Control Plans should also specify the number of times each ramp is allowed to close.
2015 | E8L99 | 415462-2 | Jaime Gomez | Mike Van Der Heyden | RS&H | All Electronic Toll (AET) Phase 4A | Construction - Extinguish the Torch Session III Report | Traffic Control Plans | Roadway | Traffic Control Plans show all pavement markings as Temporary. According to Specifications, all temporary markings shall be paint unless otherwise shown in the plans. Contract includes pay items for paint and removable tape. | EOR should provide specific locations in the Traffic Control Plans and/or notes where removable tape is to be used.
2015 | E8L99 | 415462-2 | Jaime Gomez | Mike Van Der Heyden | RS&H | All Electronic Toll (AET) Phase 4A | Construction - Extinguish the Torch Session III Report | Traffic Control Plans | Roadway | Several maintenance of traffic phases required long work zones protected by temporary concrete barrier wall without sufficient openings for construction vehicle access. | EOR should provide construction vehicle access points at 750’ intervals (approximately) in long work zones enclosed by barrier wall.
2015 | E8L99 | 415462-2 | Jaime Gomez | Mike Van Der Heyden | RS&H | All Electronic Toll (AET) Phase 4A | Construction - Extinguish the Torch Session III Report | Utility Removal | Utilities | The Utility Adjustment Plan Sheets required the removal of abandoned water and sanitary sewer service lines to a demolished toll plaza building. The Utility Work Schedule also requires the removal of these services. However, there were inconsistencies within these 2 documents as to the limits of the required removals. | Even though removal work was clearly described under the Utility Work Schedule and included as part of the Contract, the EOR should detail the utility removal work with limits shown in the Utility Adjustment Plans and, in this instance, the Toll Facilities Demolition Plans.
2015 | E8M77 | 406151-4 | Ernest Garcia | Tom Neyer | AECOM | All Electronic Toll (AET) Phase 6B | Construction - Extinguish the Torch Session III Report | Toll Gantry Cross Section | Tolls Design | A FTE review comment on a gantry shop drawing indicated “Field verify the final maximum and minimum pavement elevations below the gantry to determine the correct truss height and column lengths.” However, since fabrication and erection of the gantry must be done during an earlier phase than the paving of the roadway, it was not possible to field verify the final pavement elevations at the time that the shop drawing needed to be submitted. It was determined that elevations taken from the Contract Plans would be sufficient to determine that the shop drawings gave the correct truss height and column lengths; however the Contract Plans did not give the pavement elevations at the station where the gantry was to be constructed. | The EOR should include a specific cross section at the location of each tolling gantry. The gantry location cross section should give the profile grade elevation, as well as the high point and low point of the final pavement elevation in each direction of travel. Consider potential update to the GTR. For widening and retrofit projects, the EOR should field verify the existing pavement elevations. Ensure that the EOR has coordinated roadway, toll and structure (wall) design to confirm consistent information is being provided in each Contract Plans component set and to avoid duplicate/conflicting information.
2015 | E8M77 | 406151-4 | Ernest Garcia | Tom Neyer | AECOM | All Electronic Toll (AET) Phase 6B | Construction - Extinguish the Torch Session III Report | Noise Impacts | Tolls Design | The original Contract Plans did not require the generator enclosures to be noise attenuating. For most locations along the corridor this was not an issue; however, at one exit ramp, there is a residential home within 40 feet of the new equipment building site. Decibel readings at the property line were significantly above an acceptable threshold. | The EOR should review the locations of the equipment buildings and associated appurtances. In urban areas, with residential properties in close proximity, noise abatement measures for equipment should be considered. Consider potential update to the GTR.
2015 | E8M77 | 406151-4 | Ernest Garcia | Tom Neyer | AECOM | All Electronic Toll (AET) Phase 6B | Construction - Extinguish the Torch Session III Report | Power Service | Tolls Design | The Contract Plans for the electrical service show one electrical transformer at each toll equipment building site. At 2 sites the contract plans identified two separate electrical service meters, one installed at the equipment building and one installed for the ITS system but the 2 equipment building sites were constructed as designed with a single transformer at each building. The FTE General Tolling Requirements (GTR) requires that the toll equipment building and the ITS systems must be fed from separate electrical transformers. | The EOR should ensure that the Contract Plans incorporate all current GTR requirements in the original Design Plans. Specifically, the Contract Plans need to indicate separate electrical transformers for the Tolling Systems and for ITS components.
2015 | E8M77 | 406151-4 | Ernest Garcia | Tom Neyer | AECOM | All Electronic Toll (AET) Phase 6B | Construction - Extinguish the Torch Session III Report | Construction Sequencing | Tolls Design | After construction began, it was revealed to the CEI and contractor that a mainline toll equipment building was to be the Server site (or Primary) for six ramp equipment buildings. If equipment building sites that are dependent on the Primary are constructed prior to the Primary, they cannot be put into operation until after the Primary site is operational and interconnected. This caused significant schedule issues. FTE Tolls indicated that this issue was caused due to the change in the TEC from Raytheon to Transcore. The Contract Plans were developed for the Raytheon system, which would not have required the Primary site. | The EOR should identify the Primary and subordinate toll equipment building sites during the design effort. This information, with sequence of construction, must be denoted clearly on the Contract Plans. Conduct a construction sequencing coordinating meeting with FTE Tolls prior to the development of the 45% maintenance of traffic submittal. Consider potential update to the GTR.
2015 | E8M77 | 406151-4 | Ernest Garcia | Tom Neyer | AECOM | All Electronic Toll (AET) Phase 6B | Construction - Extinguish the Torch Session III Report | Traffic Control Plans | Roadway | It was necessary to transport sections of a mainline gantry to the project site and complete the structure’s splicing of the components there. Due to the final weight and length of the assembled structure, it was necessary to complete the assembly of the structure in the median, at the location where it was to be flown into final position. However, there was no Traffic Control Plan phase identified to stage this assembly work. | The EOR should perform early constructability reviews and be sure to include Traffic Control Plans phases to stage, construct/assemble, lift, and set large structures.
2015 | E8M77 | 406151-4 | Ernest Garcia | Tom Neyer | AECOM | All Electronic Toll (AET) Phase 6B | Construction - Extinguish the Torch Session III Report | Traffic Control Plans | Roadway | The scope of work includes the complete demolition and reconstruction of the pavement on sections of four ramps. For three of the ramps, the Traffic Control Plan required that the demolition of the old pavement and placement of new asphalt pavement, over the full 2-lane width of the ramp, be done over the course of a weekend. The contractor demonstrated that they could not perform all the work required at a given ramp with the weekend time restriction. | The EOR should carefully review the Traffic Control Plans phasing to ensure that the work is constructible within the time constraints imposed by the Traffic Control Plans, and the time constraints are reasonable for the work effort required.
2016 | E8N37 | 431123-1 | Todd Kelly | Pamela Nagot | WBQ | Polk Parkway Painting of Bridges 160257, 160258 and 164507 | Construction - Extinguish the Torch Session III Report | Traffic Control Plans | Roadway | The Traffic Control Plans assumed an existing shared thru-right lane was right-turn only; however no signage established the lane as right-turn only and if the maintenance of traffic was implemented thru traffic in the lane would enter the work zone. | The EOR should field verify maintenance of traffic schemes prior to finalizing the Contract Plans.
2016 | E8N37 | 431123-1 | Todd Kelly | Pamela Nagot | WBQ | Polk Parkway Painting of Bridges 160257, 160258 and 164507 | Construction - Extinguish the Torch Session III Report | Traffic Control Plans | Roadway | The Traffic Control Plans showed lanes open on one side of an intersection that did not line up with the lanes proposed to be open on the opposite side of the intersection, under a bridge. | The EOR should field verify maintenance of traffic schemes prior to finalizing the Contract Plans.
2016 | E8N37 | 431123-1 | Todd Kelly | Pamela Nagot | WBQ | Polk Parkway Painting of Bridges 160257, 160258 and 164507 | Construction - Extinguish the Torch Session III Report | Lighting Design | Lighting | Bridge painting contractors are typically not versed in lighting work. Within this lump sum contract’s scope, the contractor was required to provide several items for underdeck lighting: engineering drawings for structural supports, calculations, photometrics, and shop drawings. During the course of the project, the contractor realized he did not fully understand his contractual requirements and having limited experience with lighting design, was unable to locate an engineer to provide the calculations and shop drawings for such a small lighting scope. | When bridge painting is the primary scope of work, specialized activities such as pendant lighting replacement should be excluded and a separate lighting contract let prior to the painting work. If the lighting work must be included in the bridge painting contract, the lighting design (including all necessary calculations and drawings) should be completed by the EOR during the design phase of the project. A pre-bid meeting should then be held to review this component of the contract documents.
2016 | E8N37 | 431123-1 | Todd Kelly | Pamela Nagot | WBQ | Polk Parkway Painting of Bridges 160257, 160258 and 164507 | Construction - Extinguish the Torch Session III Report | Concrete Surface Finishes | Structures Maintenance | The scope of work called for the concrete surfaces to be cleaned in accordance with FDOT Standard Specification Section 400-19, which includes removal of loose coatings. The existing concrete coating was damaged by pressure washing, with the resulting cleaned surface having a very inconsistent or aged appearance. New Class 5 concrete coating was excluded from the original contract. | The EOR should evaluate the need for new Class 5 coating when adhesion of the existing coating is identified to be inconsistent during the existing conditions assessment. The new Class 5 work can be deleted if the cleaning does not damage the existing concrete surface coating.
2016 | E8N60 | 415462-6 | Jaime Gomez | Mike Van Der Heyden | RS&H | All Electronic Tolling (AET) Phase 4B | Construction - Extinguish the Torch Session III Report | Plan Notes | Tolls Design | Contract Plan note indicated that “21 consecutive days shall be allowed for each tolling movement for equipment installation and testing”. Contractor interpreted this note as needing to turn over all of the toll equipment buildings to the TEC at the same time, 21 days prior to implementation. | The EOR should modify the existing Contract Plan note to clarify that the toll equipment buildings cannot be turned over to the TEC concurrently.
2016 | E8N60 | 415462-6 | Jaime Gomez | Mike Van Der Heyden | RS&H | All Electronic Tolling (AET) Phase 4B | Construction - Extinguish the Torch Session III Report | Construction Sequencing | Roadway | After the first demolition phase at a toll plaza, as identified in the Contract Plans, numerous blunt ends were left in place. Traffic was no longer required to stop at the toll plaza, thus travel speeds through this point were higher and further exacerbated the potential hazards that were created, and left in place, by the initial demolition phase. | The EOR needs to ensure that the initial demolition phase at an existing tolling point, where AET implementation has already occurred, includes the removal of or addresses roadside hazards resulting from the demolition.
2016 | E8P54 | 431100-1 | Jaime Gomez | Scott Kamien | TLP | Resurface HEFT from MP 33.2 to MP 35.4(SB) & MP 35.4 to MP 38.0(NB) | Construction - Extinguish the Torch Session III Report | Existing Pavement Condition | Roadway | It was determined during construction that the location of the longitudinal crack, both southbound and northbound, fell within different limits than those called out in the Contract Plans. | The EOR should meet with FTE Maintenance in the field at the onset of design to determine the actual location of existing deficiencies to be addressed.
2016 | E8P55 | 435617-1 | Jaime Gomez | Terry Miller | Kimley-Horn | Arterial DMS Installation in Broward & Palm Beach Counties | Construction - Extinguish the Torch Session III Report | ITS Equipment | ITS | FTE ITS indicated that the wireless components and Managed Field Ethernet Switches (MFES) installed were not 100% compatible with the existing components they used. The Contract Plans provided no TSPs for the wireless components. The MFES were approved based on the standard specifications. | FTE ITS should provide minimum requirements to the EOR for all the equipment installed to ensure 100% compatibility with existing components and inventory.
2017 | E8Q16 | 435406-1 | Roxanne Riggs | Marco Barbarossa | Protean | Mainline Spur Painting of Bridges 870701, 870702 | Turnpike Structures | Project Team Staffing | Structures | Project team did not include structures staff. | Although there was no structural design tasks associated with the bridge painting, there was several structural POST-design tasks for which the EOR needed a structural engineer. These included review of containment shop drawings and submittals for construction loads on the bridge. EOR should have structures staff on the team for bridge painting projects.
2017 | E8Q16 | 435406-1 | Roxanne Riggs | Marco Barbarossa | Protean | Mainline Spur Painting of Bridges 870701, 870702 | Turnpike Structures | Traffic Control Plans | Roadway | MOT on the bridge was for intermittent lane closures. | During construction, the Contractor wanted to leave containment connectors on the face of the barrier. This would only be acceptable when the MOT was in place. EOR should consider adding a note to the plans to clarify that containment connections are precluded from the traffic face and top of the barrier.
2017 | E8N67 | 415051-4 | Ken Hudson | Paul Naranjo | Wantman Group | Widen HEFT Bird Rd. to SR 836 (Design-Build) | Turnpike Structures | Mass Concrete | Structures | Mass concrete was not identified in the plans. | For design-bid-build projects, the EOR designates elements that are mass concrete (as defined by the SDG) by use of the proper pay item numbers. This then triggers the required Specifications sections in construction for mass concrete. For design-build projects, the EOR is to identify mass concrete (as defined by the SDG) with plan notes that require use of the proper Specifications sections. Identification in either case requires calculations of volume to surface ratios. Mass concrete should be identified and should conform to all appropriate requirements of the Specifications regardless of project type. The only difference is how it is designated in the plans.
2017 | E8M60, E8M62, E8M63 | 431275-1, 406152-1, 406151-1 | Tracie Rose, Fernando Gomez | Tom Neyer | AECOM | Widen Veterans Expy. Sections 1-3 | Construction - Extinguish the Torch Session II Report | Traffic Control Plans | Roadway | Sawcut offsets in the Roadway Plans for inside widening were in conflict with inside temporary barrier layout in the Traffic Control Plans. This conflict required a additional MOT sub-phase during construction. | The EOR should ensure that temporary barrier wall layouts in the Traffic Control Plans are on the proper side of the sawcut line and account for the barrier wall width and required offset distance.
2017 | E8M60, E8M62, E8M63 | 431275-1, 406152-1, 406151-1 | Tracie Rose, Fernando Gomez | Tom Neyer | AECOM | Widen Veterans Expy. Sections 1-3 | Construction - Extinguish the Torch Session II Report | Profile Grade Line | Roadway | The Contract Plans did not include the profile grade line for existing pavement that was proposed to be saved by use of sawcuts. Median barrier wall was constructed using sawcut line elevations surveyed by the contractor leading to low and high walls and reveals. | The EOR should survey and provide the profile grade line on existing asphalt that is proposed to be saved.
2017 | E8M60, E8M62, E8M63 | 431275-1, 406152-1, 406151-1 | Tracie Rose, Fernando Gomez | Tom Neyer | AECOM | Widen Veterans Expy. Sections 1-3 | Construction - Extinguish the Torch Session II Report | Traffic Control Plans | Roadway | The Traffic Control Plans limited the duration of a ramp closure to 9 days, during which the work to be completed included AET gantry foundation drilled shaft and AET gantry installation. The gantry structure is not fabricated until the as-built survey of the drilled shafts is submitted to the fabricator, which can take a minimum of 6-10 weeks. The time constraint for the ramp closure did not allow for the completion of the required activities. | For ramp reconstruction with drilled shafts, AET gantry fabrication and erection, the EOR should ensure to properly sequence the construction of the roadway, the gantry foundations and the gantry erection. Temporary diversion may be required to maintain the ramp open for periods of time between operations.
2017 | E8M60, E8M62, E8M63 | 431275-1, 406152-1, 406151-1 | Tracie Rose, Fernando Gomez | Tom Neyer | AECOM | Widen Veterans Expy. Sections 1-3 | Construction - Extinguish the Torch Session II Report | Open Flume | Drainage | An open flume was constructed on a 1:2 slope and did not have curb details which resulted in water flowing over the ditch pavement which eroded the 1:2 slope. | The EOR should consider a shoulder inlet system rather than an open flume. If an open flume is determined to be the best option, it should be very carefully considered on slopes steeper then 1:6 and should be sized to contain the 10-year storm.
2017 | E8M60, E8M62, E8M63 | 431275-1, 406152-1, 406151-1 | Tracie Rose, Fernando Gomez | Tom Neyer | AECOM | Widen Veterans Expy. Sections 1-3 | Construction - Extinguish the Torch Session II Report | Shoulder Gutter | Drainage | Per the Contract Plans, temporary asphalt was placed in the existing shoulder gutter, reducing the capacity of the gutter. This resulted in the gutter overflowing during heavy rain events and causing washouts. | If the EOR calls for temporary pavement that impacts the capacity of a gutter, the EOR needs to conduct a drainage evaluation to ensure that the temporary drainage design meets criteria.
2017 | E8M60, E8M62, E8M63 | 431275-1, 406152-1, 406151-1 | Tracie Rose, Fernando Gomez | Tom Neyer | AECOM | Widen Veterans Expy. Sections 1-3 | Construction - Extinguish the Torch Session II Report | ITS Hub | ITS | Local ITS hubs and cabinets were set on pilaster mounted overhang concrete slabs set on MSE Walls, with maintenance access intended to be provided from the outside shoulder. At locations with shoulder mounted sound walls, access from the outside shoulder is problematic. | For pilaster mounted local ITS hubs in sections with shoulder mounted sound wall, the EOR should, whenever possible, locate the local ITS hubs where there are existing or proposed gaps in the sound wall or provide a maintenance berm to allow local road access via a bucket truck.
2017 | E8M60, E8M62, E8M63 | 431275-1, 406152-1, 406151-1 | Tracie Rose, Fernando Gomez | Tom Neyer | AECOM | Widen Veterans Expy. Sections 1-3 | Construction - Extinguish the Torch Session II Report | ITS Hub | ITS | Contract Plans did not provide a detail for the foundations, stairs or security fence for the ITS equipment shelter. | A standard ITS Master Hub Detail drawing needs to be developed and incorporated in all project Contract Plans which require an ITS Master Hub prefabricated shelter.
2017 | E8M60, E8M62, E8M63 | 431275-1, 406152-1, 406151-1 | Tracie Rose, Fernando Gomez | Tom Neyer | AECOM | Widen Veterans Expy. Sections 1-3 | Construction - Extinguish the Torch Session II Report | ITS Conduit | ITS | ITS fiber and electrical conduits were installed in the roadway shoulders. This complicated asphalt paving operations, often resulting in conduits being hit or crushed. | ITS fiber conduits should be buried in a duct bank near the ROW fence. If the only available option is installing the conduits in the roadway shoulder, they should be protected from damage during construction activities, such as inside and HDPT duct or concrete trench.
2017 | E8P84 | 435604-1 | Jaime Gomez | Andy Healy | HDR | CCTV Camera Installation Turnpike Wide | Construction - Extinguish the Torch Session II Report | Cross Sections | ITS | A number of CCTV poles were set near the top of the embankment at the bridges. This becomes difficult to directional bore, due to the height of embankment, MSE walls which extend into the ground, and the space required for the equipment and required distance for the sweep. Pull boxes were set next to the CCTV poles at the top of the high fill. Consideration for those performing maintenance needs to be taken into consideration in placing the pull boxes. | The Contract Plans should include cross sections at high fill areas in order to be able to help identify issues related to design and maintenance of ITS infrastructure placed in these areas.
2017 | E8P84 | 435604-1 | Jaime Gomez | Andy Healy | HDR | CCTV Camera Installation Turnpike Wide | Construction - Extinguish the Torch Session II Report | Sodding | ITS | The installation of conduit for the CCTV poles required trenching up a slope of 1:2. The restoration of the slope required additional sodding, beyond what is provided per Specification for pole installation and trenching, to address erosion prone areas. | The EOR needs to assure that detailed quantities for sod are provided for the restoration of erosion prone areas.
2017 | E8P84 | 435604-1 | Jaime Gomez | Andy Healy | HDR | CCTV Camera Installation Turnpike Wide | Construction - Extinguish the Torch Session II Report | Site Verification | Project Team | A number of pull boxes and splice vaults were shown on the Contract Plans, but were difficult to locate, being buried under dirt or asphalt, or were not found at all during construction. At an interchange area, land use shown on the Contract Plans was found to be different from existing site conditions, also landscaping was present that was not reflected in the Plans. The Contract Plans misidentified an FTE ITS splice vault that was actually a utility vault. | The EOR should conduct an in-depth site review to verify existing elements included from previous as-built plans and to identify any changes to the existing as-built plans that should be reflected in the Contract Plans.
2017 | E8P84 | 435604-1 | Jaime Gomez | Andy Healy | HDR | CCTV Camera Installation Turnpike Wide | Construction - Extinguish the Torch Session II Report | Cross Sections | ITS | The Contract Plans included directional boring under a canal, but a permit was not obtained from the local water management district. Due to the steepness of the angle needed for placement, directional boring could not be performed. | The Contract Plans should include cross sections where directional boring is proposed under canals or box culverts in order to help identify issues in performing the boring and to highlight the need for potential permitting activities. The cross sections should include minimum clearances required from the bottom of the canal.
2017 | E8P84 | 435604-1 | Jaime Gomez | Andy Healy | HDR | CCTV Camera Installation Turnpike Wide | Construction - Extinguish the Torch Session II Report | Power Service | Electrical | The Contract Plans proposed a new electrical service with meter and disconnect when another ITS service was located within 500 feet of the proposed location. There are other factors that may have been considered (i.e. voltage drop) that could have affected whether the existing service could be used. | The EOR should complete a constructability review prior to finalizing plans that verifies the cost effectiveness of proposed improvements, including coordination of power service with the service provider and other disciplines to determine the best solution for service.
2017 | E8P84 | 435604-1 | Jaime Gomez | Andy Healy | HDR | CCTV Camera Installation Turnpike Wide | Construction - Extinguish the Torch Session II Report | Legacy Devices | ITS | The Contract Plans did not propose any upgrades to existing equipment when some of the legacy devices were at the end of their life cycle. | The EOR should provide feedback regarding the condition of existing devices and provide an option to upgrade devices as necessary.
2018 | E8P94 | 432827-1, 432827-3 | Todd Kelly | Snehal Ambare | Moffatt & Nichol | Resurface Mainline in Osceola Co. from MP 238.76 to MP 248.50 | Construction - Extinguish the Torch Report | Traffic Control Plans | Roadway | The Contract Plans included a temporary traffic diversion that did not account for a conflicting bridge pier, which didn't allow for required lane widths. | The EOR should account for any conflicts when designing traffic diversions.
2018 | E8P94 | 432827-1, 432827-3 | Todd Kelly | Snehal Ambare | Moffatt & Nichol | Resurface Mainline in Osceola Co. from MP 238.76 to MP 248.50 | Construction - Extinguish the Torch Summary Report | Temporary Drainage Structures | Drainage | The Contract Plans included a temporary drainage structures that conflicted with the toe of slope of a temporary traffic diversion, resulting in the need for a slope greater than 1:4 to avoid the temporary drainage inlet. | The EOR should consider providing cross sections for temporary drainage structures in conjunction with temporary traffic diversions.
2018 | E8P94 | 432827-1, 432827-3 | Todd Kelly | Snehal Ambare | Moffatt & Nichol | Resurface Mainline in Osceola Co. from MP 238.76 to MP 248.50 | Construction - Extinguish the Torch Summary Report | Traffic Control Plans | Roadway | The Contract Plans did not provide MOT details for lane closures on the local roadway which were required for ramp milling & resurfacing and no coordination was conducted with local agency. | The EOR should include MOT details for paving near ramp terminals and be sure to coordinate MOT with local agency.
2018 | E8P94 | 432827-1, 432827-3 | Todd Kelly | Snehal Ambare | Moffatt & Nichol | Resurface Mainline in Osceola Co. from MP 238.76 to MP 248.50 | Construction - Extinguish the Torch Summary Report | Traffic Signals | Signalization | Advance loops for a signalized ramp terminal were removed during a paving operation but the Contract Plans did not call for their replacement, impacting the operation of the ramp terminal signals. | The EOR should evaluate and account for existing signal loops.
2018 | E8P90 | 435615-1, 435615-4 | Roxanne Riggs | Terry Miller | Kimley-Horn | Mainline at Glades Rd. NB Exit Ramp & Intersection Improvements (MP 75) | Construction - Extinguish the Torch Summary Report | Irrigation | Landscaping | The Contract Plans called for capping existing irrigation in the median of the local roadway where there was grass that required irrigation and an existing local Maintenance Agreement. | For projects with irrigation impacts on local roadways, need to determine if a Maintenance Agreement exists and coordinate with impacted parties.
2018 | E8P90 | 435615-1, 435615-4 | Roxanne Riggs | Terry Miller | Kimley-Horn | Mainline at Glades Rd. NB Exit Ramp & Intersection Improvements (MP 75) | Construction - Extinguish the Torch Summary Report | Traffic Control Plans | Roadway | The Contract Plans called for inside and outside widening and milling and resurfacing for cross-slope correction and to gain wall reveal. The Plans called for outside widening first but did not indicate which phase to complete the milling and resurfacing. This created the concern of drop-offs created during the outside widening. | The EOR should design the construction phasing with the milling and resurfacing, with cross-slope correction, completed first then accomplish the widening.
2018 | E8P90 | 435615-1, 435615-4 | Roxanne Riggs | Terry Miller | Kimley-Horn | Mainline at Glades Rd. NB Exit Ramp & Intersection Improvements (MP 75) | Construction - Extinguish the Torch Summary Report | Sodding | Roadway | The Contract Plans did not include performance turf for areas that needed to be restored outside of the limits of clearing and grubbing. | The EOR should consider and account for all areas where sodding is required, not just within the limits of clearing and grubbing.
2018 | E8P90 | 435615-1, 435615-4 | Roxanne Riggs | Terry Miller | Kimley-Horn | Mainline at Glades Rd. NB Exit Ramp & Intersection Improvements (MP 75) | Construction - Extinguish the Torch Summary Report | Slope Reinforcement | Maintenance | Existing geogrid slope reinforcement (installed as an iguana deterrent) was encountered during clearing and grubbing. The Contract Plans did not indicate the existence of the geogrid or identify any need to replace. | FTE Maintenance should coordinate with the EOR regarding the presence of existing slope reinforcement and to consider if iguana deterrent/treatments are needed.
2018 | E8P90 | 435615-1, 435615-4 | Roxanne Riggs | Terry Miller | Kimley-Horn | Mainline at Glades Rd. NB Exit Ramp & Intersection Improvements (MP 75) | Construction - Extinguish the Torch Summary Report | Traffic Signals | Signalization | The Contract Plans called for Adaptive Control equipment at two intersections, with the understanding the local agency would have implemented Adaptive Control at these locations prior to the project. The County did not complete the work as planned, and installing only the partial equipment provided in the Contract would not allow signals to operate properly. | Where work is to be completed by another agency prior to the beginning of the project, the EOR should coordinate to determine the status of the work prior to letting.
2019 | E8Q41 | 435165-1, 435165-3, 435167-1, 435167-3 | Christopher NeSmith | Steve Soldati | CES | Resurface Mainline in Okeechobee & Indian River Counties from MP 178.2 to MP 185.0 | Construction - Extinguish the Torch Summary Report | Traffic Control Plans | Roadway | Base failures occurred in deep mill asphalt sections. A contributing factor was determined to be insufficient cooling time for the thick asphalt mat. After evaluating a test section, it was determined that 6 hours was the max cooling time. | For projects where there is a potential for base failures, the EOR should account a 6-hour cooling in the design of the traffic control plans.
2019 | E8Q41 | 435165-1, 435165-3, 435167-1, 435167-3 | Christopher NeSmith | Steve Soldati | CES | Resurface Mainline in Okeechobee & Indian River Counties from MP 178.2 to MP 185.0 | Construction - Extinguish the Torch Summary Report | Milling Depth | Roadway | The Contract Plans included 30 different typical sections for milling depths and cross slope correction. Time consuming and confusing for the Contractor to cross reference multiple sheets to determine the appropriate construction sequence. | The EOR should prepare a single page summary exhibit displaying the proposed milling depth and cross slope correction throughout the entire project limits. Do not rely soley on shading to differentiate and identify different pavement depths or ranges.
2019 | E8Q41 | 435165-1, 435165-3, 435167-1, 435167-3 | Christopher NeSmith | Steve Soldati | CES | Resurface Mainline in Okeechobee & Indian River Counties from MP 178.2 to MP 185.0 | Construction - Extinguish the Torch Summary Report | Bridge Joints | Structures | To place the polymer nosing for bridge joints, the asphalt had to be removed all the way to the bridge deck because the polymer nosing will not adhere to asphalt. The thickness of polymer nosing in the Contract Plans was calculated using the 2.25” mill depth rather than using the full depth of the asphalt on the bridge deck. Since the asphalt was much thicker than 2.25” mill depth, the quantity for the polymer nosing had to be significantly overrun. | The EOR should review asphalt pavement condition reports to determine the existing thickness over the bridge decks and the polymer nosing depth for bridge joints should be established based on existing asphalt thickness.
2019 | E8Q77 | 439051-1 | Christopher NeSmith | Steve Soldati | Vibe | ITS Electrical Improvements from MP 185 to MP 235 | Construction - Extinguish the Torch Summary Report | Existing Electrical Service Components | ITS | The Contract Plans did not include the replacement of existing electrical service disconnect boxes and conduit at those boxes at any ITS pole locations. After construction started, it was determined that the existing disconnect boxes were in poor condition and the disconnect boxes and the conduit did not meet current code. | The EOR should conduct a thorough on-site review of existing features to assess their condition and determine the benefit of replacing with new features.
2019 | E8Q77 | 439051-1 | Christopher NeSmith | Steve Soldati | Vibe | ITS Electrical Improvements from MP 185 to MP 235 | Construction - Extinguish the Torch Summary Report | Existing Drainage Structures | Drainage | The Contract Plans indicated open trenching of conduit that conflicted with existing storm drains and drainage features. | The EOR should conduct a thorough review and inspection of existing features, which includes review of existing plans in addition to a field review of the corridor.
2019 | E8N19 | 429350-1 | Tracie Rose | Tom Neyer | TY Lin | Widen Veterans Expy. from Gunn Hwy. to Sugarwood ML Plaza (MP 9.0 to MP 10.727) | Construction - Extinguish the Torch Summary Report | Project Limits | Project Manager | The end of an adjacent project and beginning of this project was located near a bridge structure, which was difficult to coordinate construction phases and transition of traffic approaching and over the bridge. | When possible, locate the point of interface between two adjacent projects away from bridge structures.
2019 | E8N19 | 429350-1 | Tracie Rose | Tom Neyer | TY Lin | Widen Veterans Expy. from Gunn Hwy. to Sugarwood ML Plaza (MP 9.0 to MP 10.727) | Construction - Extinguish the Torch Summary Report | Concrete Surface Finishes | Structures Maintenance | The Contract Plans included an overhead sign structure with concrete columns that extended to the top of an adjacent MSE wall. The MSE wall required a Class V finish but the concrete column did not require any Class V finish, creating an aesthetic issue. | The EOR should identify adjacent concrete structures and determine if the application of consistent surface finish treatments is appropriate.
2019 | E8N52 | 429350-4 | Tracie Rose | Tom Neyer | GAI | Widen Veterans Expy. from Sugarwood ML Plaza to Van Dyke Rd. (MP 10.823 to MP 14.204) | Construction - Extinguish the Torch Summary Report | Project Limits | Project Manager | The Design-Build RFP required the D-B Team to implement Express Lanes outside of the limits of widening and what was designated as the construction limits. | D-B RFP language should ensure that any work required is within the specified construction limits.
2019 | E8N52 | 429350-4 | Tracie Rose | Tom Neyer | GAI | Widen Veterans Expy. from Sugarwood ML Plaza to Van Dyke Rd. (MP 10.823 to MP 14.204) | Construction - Extinguish the Torch Summary Report | Power Service | Electrical | The Contract Plans indicated that the conductors from the utility transformer to the meter at the load center would be installed by the utility provider. During inspection and activation of the power service, the utility provider indicated this was not their responsibility. | The EOR should ensure that the installation of conductors for electrical service from the utility service transformer to the meter/load center are shown to be installed by the contractor, per TDH Lighting & Electrical Guide Drawings and FDOT Specifications.
2019 | E8P07 | 4356090-1 | Tracie Rose | Tom Neyer | AECOM | Express Lanes Implementation on Veterans Expressway MP 2.911 to MP 10.358 | Construction - Extinguish the Torch Summary Report | ITS Conduit | ITS | The Contractor encountered multiple issues during the installation of the larger size wiring needed for the ITS devices on the project due to the size and condition of existing conduit. | The EOR should review typical conduit sizes for locations where wire size has increased and determine if conduit may need to be larger. The EOR should verify the condition of existing conduit and verify if spare conduit is still available prior to identifying its use for future projects.
2019 | E8P07 | 4356090-1 | Tracie Rose | Tom Neyer | AECOM | Express Lanes Implementation on Veterans Expressway MP 2.911 to MP 10.358 | Construction - Extinguish the Torch Summary Report | ITS Cabinet | ITS | The Contract Plans added a DMS to a site with an existing DMS and proposed using the existing cabinet and existing pull box. The equipment and wiring for the new DMS would not fit in the existing cabinet or be accommodated in the existing pull box. | The EOR should verify the equipment already in an existing cabinet and pull box and determine if they can accommodate required additional equipment and wiring.
2019 | E8P07 | 4356090-1 | Tracie Rose | Tom Neyer | AECOM | Express Lanes Implementation on Veterans Expressway MP 2.911 to MP 10.358 | Construction - Extinguish the Torch Summary Report | Power Service | Electrical | The existing lighting load centers did not have disconnect switches at the power meters adjacent to the utility provider power poles. Power was turned off to replace the existing load center cabinets with new cabinets, but the utility provider would not turn back on the power until new disconnect switches were provided that met current standards. The Contract Plans: did not include disconnect switches; show existing disconnects to remain; and include an inconsistency between the riser diagram and the wiring schematic detail (which shows two disconnects existing to remain). | The EOR should assess existing load centers to see if they have disconnect switches between the meter and the load center panel and if so determine if the load centers meet current standards. TDH Lighting & Electrical Guide Drawings show a service disconnect on the load side of the meter.
2019 | E8P07 | 4356090-1 | Tracie Rose | Tom Neyer | AECOM | Express Lanes Implementation on Veterans Expressway MP 2.911 to MP 10.358 | Construction - Extinguish the Torch Summary Report | Express Lanes | Roadway | The Contract Plans included an entrance point and an exit point of an express lanes in a curve. | The EOR should evaluate the location of the entrance and exit points of express lanes and where possible, they should be located in tangent sections.
2019 | E8R64 | 442631-1 | Tracie Rose | Jason Christopher | AECOM | Veterans Expressway Improvements for Bridge Approaches | Construction - Extinguish the Torch Summary Report | Approach Slab | Structures | The Contract Plans called for hydrodemolition of an approach slab due to coring data that seemed to indicate shallow rebar depth. During construction the rebar depth was found to be greater than anticipated resulting in a significantly longer hydrodemolition duration and the determination that full slab replacement would have been more efficient. | In situations where hydrodemolition is being considered the EOR should be sure to have enough data to ensure an accurate gauge of rebar depth over the entire slab.
2019 | E8R64 | 442631-1 | Tracie Rose | Jason Christopher | AECOM | Veterans Expressway Improvements for Bridge Approaches | Construction - Extinguish the Torch Summary Report | Traffic Control Plans | Roadway | The Contract Plans called for hydrodemolition of approach slab shoulder and 2 lanes to occur with live traffic directly adjacent to the operation. This posed safety concerns of projectiles hitting vehicles and safety of workers given a lack of buffer area. The work area was decreased in width to provide space for a protection shield and safety of the workers replacing the slab during pouring of concrete. Also, approval was given during construction to close a third lane in order to pour back concrete. | The EOR should prepare MOT plans which take into account the necessary buffer space (recommend min. 5’) for the hydrodemolition equipment and for screeding and finishing the concrete.
2019 | E8R64 | 442631-1 | Tracie Rose | Jason Christopher | AECOM | Veterans Expressway Improvements for Bridge Approaches | Construction - Extinguish the Torch Summary Report | Concrete Grooving | Structures | The Contract Plans called for hydrodemolition and concrete replacement in all lanes of an approach slab to occur over a single weekend. In addition, the Plans called for a Class 4 finish and grooving of the approach slab concrete. Due to constraints of lane closure restrictions, mechanical grooving could not be performed prior to opening the travel lanes. requiring manual tining to be performed. | In establishing lane closures, the EOR should ensure that there is enough time for placing and curing of concrete to allow for mechanical grooving per specifications.
2019 | E8R64 | 442631-1 | Tracie Rose | Jason Christopher | AECOM | Veterans Expressway Improvements for Bridge Approaches | Construction - Extinguish the Torch Summary Report | Traffic Control Plans | Roadway | The Contract Plans traffic control required two lanes to be open at all times during construction operations. The project corridor includes 3 general toll lanes and 1 express lane. The express lane ingress was several miles away from the work zone, thus when closures were necessary for the outside lanes the traveling public experienced delays due to the inability to access the express lane and functionally only one lane open to traffic. | The EOR needs to account for the unique operational and access characteristics of express lanes in developing traffic control plans within active express lane corridors.
2019 | E8R57 | 442901-7 | Christopher NeSmith | Anil Sharma | Protean | Emergency Shoulder Use Mainline NB MP 140 to MP 210 | Construction - Extinguish the Torch Summary Report | Rumble Strips | Roadway | The Contract Plans included control points that placed the edge of the widening in the center of existing rumble strips. This would have left a portion of the existing rumble strips in place. | The EOR should not rely on as-built information for the development of the Contract Plans. Survey should be performed to locate the existing rumble strips.
2019 | E8R57 | 442901-7 | Christopher NeSmith | Anil Sharma | Protean | Emergency Shoulder Use Mainline NB MP 140 to MP 210 | Construction - Extinguish the Torch Summary Report | Traffic Control Plans | Roadway | The Contract Plans included the installation of a temporary crash cushion on a bridge. Because the crash cushion requires bolts/anchors to be installed there is the potential to impact the bridge. | The EOR should not propose crash cushions to be installed on bridges unless it is unavoidable.
2019 | E8R57 | 442901-7 | Christopher NeSmith | Anil Sharma | Protean | Emergency Shoulder Use Mainline NB MP 140 to MP 210 | Construction - Extinguish the Torch Summary Report | Rumble Strips | Roadway | The EOR assumed the edge of the existing friction course was at the edge of the lane; however, the friction course was offset from the lane similar to an 8” overlap. Also, the inside yellow lane line was designed to transition to the left over 200 to 300 feet; however, the friction course did not include the 200 to 300 foot transition. Per the Contract Plans, either the rumble strips would have been too far from the lane line in the transitions or the rumble strips would have had to transition through the friction course. | The EOR should consider the placement of friction course and rumble strips in transition areas and ensure that rumble strips can be installed according to Standard Plans without cutting through the friction course. Details should be provided for this condition.
2019 | E8R59 | 442901-8 | Christopher NeSmith | Anil Sharma | Protean | Emergency Shoulder Use Mainline NB MP 210 to MP 249 | Construction - Extinguish the Torch Summary Report | Pavement Design | Roadway | The Contract Plans typical section indicates different optional bases and structural course for the widening of the travel lane versus a new 4' inside shoulder. There are constructability issues associated with the narrow strip of construction needed for the differential design of the travel lane widening. | The EOR should consider the same typical section for travel lane widening and shoulder work when the total width of construction is less than 8’. For ease of construction and simplified paving operations, factor paving efficiency over standard shoulder design criteria in such narrow width pavement areas. This applies to narrow width shoulders, 4' or less, paved with the adjacent travel lane, and other narrow geometry correction locations at transitions, ramps, or gores. Paving efficiency and simplified paving operations also relate to TTCP plan decisions regarding work zones with overnight lane closures, compared to work zones behind temporary barrier wall.
2019 | E8R59 | 442901-8 | Christopher NeSmith | Anil Sharma | Protean | Emergency Shoulder Use Mainline NB MP 210 to MP 249 | Construction - Extinguish the Torch Summary Report | Rumble Strips | Roadway | The Contract Plans indicate the cross-slope break between the original travel lane and original outside shoulder (2% to 6%) was to remain at the original location with permanent traffic shifted to the left, away from the break. This required the rumble strips to cross the shoulder break, which doesn't meet design criteria. | In this situation the EOR should relocate the shoulder break in relation to the new edge of the outside travel lane to avoid rumble strips crossing into the shoulder break.
2020 | E8Q92 | 437988-1, 437988-3 | Christopher NeSmith | Jason Christopher | Connelly & Wicker | Resurface Mainline in Lake County from MP 287.8 to MP 297.9 | Construction - Extinguish the Torch Summary Report | Utility Adjustments | Utilities | The Contract Plans included the adjustment of AT&T manholes to be performed by the Contractor. AT&T agreed to perform any adjustments needed. | For impacts to AT&T utilities, the EOR should coordinate with AT&T concerning who will perform the work and obtain a utility work schedule if needed.
2020 | E8Q92 | 437988-1, 437988-3 | Christopher NeSmith | Jason Christopher | Connelly & Wicker | Resurface Mainline in Lake County from MP 287.8 to MP 297.9 | Construction - Extinguish the Torch Summary Report | Construction Access | Roadway | The Contract Plans included repairs to box culverts where existing dense vegetation and steep slopes were not considered relative to the ability of trucks to access the culverts. Due to steep slopes at some locations, the gunite trucks would have to be located on the edge of the roadway to be able to pump into the box culverts, requiring barrier wall and traffic shifts. | The EOR should evaluate box culvert repair sites for truck access. If necessary, establish Selective Clearing and Grubbing limits and restoration to assure access is possible or include guardrail removal/replacement and placing barrier wall, which would include a lane shift, for culverts which are inaccessible from below.
2020 | E8Q92 | 437988-1, 437988-3 | Christopher NeSmith | Jason Christopher | Connelly & Wicker | Resurface Mainline in Lake County from MP 287.8 to MP 297.9 | Construction - Extinguish the Torch Summary Report | Rumble Strips | Roadway | The Contractor submitted an RFI for what satisfies the requirement for covering of rumble strips and how it would be paid. | The EOR should specify the cost of filling in rumble strips under 102-2 Special Detour (Lump Sum). The Contract Plans should not quantify temporary asphalt tonnage; however, the Plans should provide width, length, and thickness information so that the Contractor knows the work required by this Special Detour.
2020 | E8Q92 | 437988-1, 437988-3 | Christopher NeSmith | Jason Christopher | Connelly & Wicker | Resurface Mainline in Lake County from MP 287.8 to MP 297.9 | Construction - Extinguish the Torch Summary Report | Embankment | Roadway | The Contract Plans called for inside shoulder treatment per Standard Index 105, Type I. In much of this the non-paved shoulder was being adjusted and required additional fill. This additional fill would not be part of a Type I treatment and was not quantified in the Plans. | When there is embankment shown for shoulder work, the EOR needs to quantify an amount and list it as embankment. The EOR needs to specify Type II Treatment when the area requires fill.
2020 | E8R76 | 439457-1 | Christopher NeSmith | Brandon Bobo | Cumby & Fair | Reconstruct Mainline in Orange County from MP 269.4 to MP 273.3 | Construction - Extinguish the Torch Summary Report | Traffic Control Plans | Roadway | The project section consisted of four lanes in each direction. Without shifting traffic, resurfacing the 2nd lane would have placed workers directly next to the third lane, requiring three lanes to be closed. Due to heavy traffic, a triple-lane closure would have significantly shortened available work time. At certain points in the project, the Contract Plans Traffic Control Plan required the lanes to be shifted onto the shoulder to resurface the 2nd lane, maintain two open lanes, and provide workers with a safe buffer from the open traffic lanes. The resurfacing required a drop-off between resurfaced lanes and the lanes that had not yet been resurfaced. Prior to shifting traffic, the drop-off was at the lane line; however, once the traffic shift was installed, the drop-off was between the vehicles tires. Complaints came in from various travelers on the roadway that the ride was uncomfortable and the condition was perceived to be unsafe. | For projects with deep milling on sections of four or more lanes, the EOR should prepare a Traffic Control Plan that provides traffic shifts, including the use of buffer zones if needed, to assure the drop-offs are contained at the lane lines and that provide for smooth transitions when having to travel across the areas with the drop-offs to the next area where work has not been performed.
2020 | E8R76 | 439457-1 | Christopher NeSmith | Brandon Bobo | Cumby & Fair | Reconstruct Mainline in Orange County from MP 269.4 to MP 273.3 | Construction - Extinguish the Torch Summary Report | Shoulder Cross Slope | Roadway | After resurfacing of the shoulder, water was being retained within the shoulder area, which had not been an existing issue at this location. When the contractor placed temporary pavement to shift traffic onto the shoulder, the existing shoulder slope which included a break, was lost. The contractor continued paving through this section at the same slope as the shoulder coming into where the existing break needed to occur. | The EOR should provide enough detail such that the existing shoulder break condition is clearly depicted or stated in the Contract Plans. The use of "match existing" call-outs do not suffice to provide the necessary information for the contractor to match the existing shoulder conditions.
2021 | E8Q12 | 411406-1, 411406-4 | Fernando Gomez | Snehal Ambare | WGI | Turnpike Widening from Osceola Pkwy to Beachline Expy | Construction - Extinguish the Torch Summary Report | Lane Closures | Traffic Operations | During construction it was anticipated that the plan-specified lane closure hours would be utilized for the necessary detours. This assumption was incorrect and more restrictive detour hours were implemented. | When detours are necessary on a project, ensure the allowable detour hours are specified in the bid documents for road and ramp closures.
2021 | E8Q12 | 411406-1, 411406-4 | Fernando Gomez | Snehal Ambare | WGI | Turnpike Widening from Osceola Pkwy to Beachline Expy | Construction - Extinguish the Torch Summary Report | Lighting Design | Lighting | A specific plan detail was missing on how the internal girder lighting conduits should be routed to the external power source. Reference RFI 513 & 513A. | Design EOR to provide supplemental design details in the plans showing locations and details of conduit runs, power sources, electrical components, and any incidental items needed for completion of box girder lighting systems, in accordance with Department requirements. Coordination between Lighting/Electrical and Structures disciplines required. See FDOT Standard Plan 715-240 and SPI 715-240 (Standard Plan Instructions) for additional information.
2021 | E8Q12 | 411406-1, 411406-4 | Fernando Gomez | Snehal Ambare | WGI | Turnpike Widening from Osceola Pkwy to Beachline Expy | Construction - Extinguish the Torch Summary Report | Concrete Pavement | Roadway | The plan typical sections for concrete pavement specify placing an Optional Base Group 1 (Type-B 12.5) under Plain Cement Concrete Pavement (9 ½”). The associated concrete shoulders that are 5’ or wider are constructed with a variable depth concrete pavement from 9 ½” to 6”. The plans did not specify that the added base under the variable depth should be incidental to the base construction and the contractor requested compensation since the item is paid by the square yard and is a plan quantity item. | Future contracts that utilize concrete pavement with tapered shoulders should include a note on the typical sections that states the base wedge is incidental to the base item.
2021 | E8R51 | 441322-1 | Fernando Gomez | Francisco Cardona / Ruby Monsalve | Hardesty & Hanover | AET Northern Coin Conversion | Construction - Extinguish the Torch Summary Report | Barrier Wall | Roadway | The contractor was required to leave approximately 5,000 feet of Type K Barrier Wall in place along both sides of the median for future use. The plans did not address any special requirements for the wall to remain – no condition requirements, no class 5 finish, no requirement that it be new wall, etc. This created much debate from the contractor in the closeout process. | Since this wall is a semi-permanent feature until removed for a future widening, the project would have benefited from having a specific item for this wall to remain so the contractor could have bid the cost of new wall eliminating controversy and providing a better product.
2021 | E8Q95 | 436520-1 | Christopher NeSmith | Jason Christopher | PGA | Ressurface Polk Parkway MP 0 to MP 8 | Construction - Extinguish the Torch Summary Report | Modeling | Roadway | Occasionally during operation, the AMG equipment would suddenly send the miller or paver to an unusual milling depth or asphalt grade. | EOR to ensure all lines/triangles are connected and no gaps or irregularities on the 3D surfaces.
2021 | E8Q95 | 436520-1 | Christopher NeSmith | Jason Christopher | PGA | Ressurface Polk Parkway MP 0 to MP 8 | Construction - Extinguish the Torch Summary Report | Lane Widths | Roadway | When comparing the measured quantities of milling and paving to the SQ sheets we have found substantial differences resulting in significant quantity overruns of approximately $292K combined. All lane widths were measured during each operation by the Contractor QC and the CEI VT. Our The field measured quantities do not match the SQ sheets because the Model and measured lane widths differ. | The lane widths in the model should be set at 12 foot exact, not match existing survey/topo/3D.
2024 | Various | Various | NA | NA | Various | Underdeck Lighting (Spec 715 - Highway Lighting) | Turnpike Structures | Lighting Design | Lighting | The APL options for "LED Luminaire, (Underdeck)" now include wall-mounted fixtures that extend much further (2.5 ft +) than their predecessors. They are being designed (photometrics) and detailed to be mounted to pier caps and/or MSE copings without verification (or documentation) or enough plan dimensions to ensure the proposed fixture meets the clearance requirements (vertical, horizontal, lateral offset) specified by FDM. | The lighting and structural EOR should coordinate on the determination of lighting mounting heights on bridge elements to ensure the proposed fixture meets the clearance requirements (vertical, horizontal, lateral offset) specified by FDM. Please pay special attention to FDM 260.6 and its figures and consider tilt angles and fixture size. Plan details and tables must provide adequate dimensions and information to ensure the Contractor will position the fixture so that it meets both the required clearances and the photometric design assumptions. The lighting design documentation should include calculations, sketches, survey info, etc. to show that the proposed design meets criteria.